## Sheet1
Week 1
| Sprint 1 | Complete | Duration | Priority | Links To | Extra Details
| Create Astah Models (Class Diagram, Sequence, etc.) | Yes | 6 hours | High | - | Class Diagram, Sequence, etc.
| Setup and Map Database | Yes | 4 hours | High | Main | Mapped Database to SQLite File and set up Foreign Keys constraints + Java Class
| Setup Classes: LeaseData -> Hall, Room, Student, Statuses | Yes | 3 hours | High | Main | Setup Java Classes to handles instances of Table elements within the Database
| Setup GUI Base | Yes | 2 hours | High | Main | Created a GUI base which is the superior
-
Week 2
| Sprint 2 | Complete | Duration | Priority | Links To | Extra Details
| Create Login Template GUI | Yes | 3 hours | High | GUI Base | Created the fundamentals of the Login GUI including Database calls
| Design Browser Template GUI | Yes | 6 hours | High | GUI Base | Created the design of the Browser GUI and made a mock-up version in JavaFX
| Design Administrator Panel GUI | Yes | 3 hours | Low | GUI Base | Created the design of the Admin Panel GUI using a TabPane and setup TableViews
| Design ViewLease GUI (Design) | Yes | 6 hours | High | GUI Base | Created the design of the ViewLease GUI with all form elements
| Created Stylesheets for each of the GUIs | Yes | 5 hours | Medium | GUI Base | Wrote out all of the stylesheets for each individual GUI component and form
Week 3
| Sprint 3 | Complete | Duration | Priority | Links To | Extra Details
| Create TableView Objects for Browser GUI | Yes | 6 hours | Medium | Browser GUI | Implemented the TableView for the Browser GUI
| Link TableView Objects to ViewLease GUI | Yes | 3 hours | High | Browser/ViewLease GUI | Linked the TableView Rows to the Database Data
| Modify and Update Administrator Panel GUI | Yes | 3 hours | Low | Admin GUI | Linked the TableView Rows in Admin Panel to the Database Data
| Start Form Validation for ViewLease GUI Inputs | Yes | 2 hours | Medium | ViewLease GUI | Added Form Validation for when editing inputs
-
Week 4
| Sprint 4 | Complete | Duration | Priority | Links To | Extra Details
| Improve ViewLease to handle edits | Yes | 2 hours | High | ViewLease GUI | Modify the elements within the GUI to handle editing
| Create handlers in Database Class | Yes | 2 hours | High | Database | Create methods that handle Lease Data objects for create/edit/delete
| Setup User Permissions for logged in users | Yes | 4 hours | High | Database/User | Retrieve User Permissions when a User Logs In
| Map out User Permissions | Yes | 1 hour | Medium | User | Map out permissions for use in TableViews on Administrator Panel GUI
-
Week 5
| Sprint 5 - Final Touches | Complete | Duration | Priority | Links To | Extra Details
| Add Right-Click Context Menu for Ease on TableView | Yes | 3 hours | Low | Browser GUI | Right-click Context Menu that allows users a quicker way to see lease information
| Add Searching Options | Yes | 4 hours | Low | Browser GUI | Added a Search Button that will filter out leases in correspondence to the search
| Finalise Administrator Panel GUI | Yes | 6 hours | Medium | Admin GUI | Finished the creation/modification/deletion of data via TableView/Database
| Finalise Browser GUI | Yes | 4 hours | High | Browser GUI | Finalise and comment the code. Remove any bugs found.
| Finalise Project | Yes | 1.5 hours | High | - | Finalise the entire project. Check for bugs, incorrect methods, unused data, etc.